## 2-Weeks Iteration
Burndown Chart
|  |  |  | Iteration | 1 |  |  |  | Noteworthy Metrics
|  |  |  | Team: | Test Team |  |  |  | C/P | REM | END | STI
1 | Team Name | Test Team |  | Today: | 2015-10-14 16:47 |  |  |  | 50% | 6 | 16 | 0.77778
2 | Iteration # | 1
3 | SP Planned | 12
4 | Start Date | 2015-10-02 |  |  | Questions? Contact @AgileStream
|  | Story Points | [5 empty] | Computed Stack
| Standup | 5. Changes | 6. Completed |  | Actual | Optimal | Today | 8 | Days from planning
| 1 | 0 | 0 |  | 12 | 12 | 0 | -0.8 | Slope Actual
| 2 | 0 | 0 |  | 12 | 10.5 | 0 | -1.5 | Slope Optimal
| 3 | 0 | 2 |  | 10 | 9 | 0 | 13.5 | Y Optimal
| 4 | 0 | 0 |  | 10 | 7.5 | 0 | 13.1111 | Y Actual
| 5 | 0 | 0 |  | 10 | 6 | 0 | 16 | X Actual
| 6 | 0 | 2 |  | 8 | 4.5 | 0 | 9 | X Optimal
| 7 | 0 | 0 |  | 8 | 3 | 0 | 0.77778 | Stream Turbulence Index
| 8 | 0 | 2 |  | 6 | 1.5 | 17
| 9 | 0 | 0 |  | 6 | 0 | 0
Note on L4: ElFakih, Adonis: Completed versus planned
Note on M4: ElFakih, Adonis: Remaining Story Points
Note on N4: ElFakih, Adonis: Forecasted End Date
Note on O4: ElFakih, Adonis: Stream Turbulence Index - % deviation from plan

## 3-Weeks Iteration
Burndown Chart
|  |  |  | Iteration | 1 |  |  |  | Noteworthy Metrics
|  |  |  | Team: | Test Team |  |  |  | C/P | REM | END | STI
1 | Team Name | Test Team |  | Today: | 2015-10-14 16:47 |  |  |  | 35.56% | 29 | 36 | 1.5714
2 | Iteration # | 1
3 | SP Planned | 45
4 | Start Date | 2015-09-30 |  |  | Questions? Contact @AgileStream
|  | Story Points | [5 empty] | Computed Stack
| Standup | 5. Changes | 6. Completed |  | Current | Optimal | Today | 10 | Days from planning
| 1 | 0 | 0 |  | 45 | 45 | 0 | -1.2923 | Slope Actual
| 2 | 0 | 0 |  | 45 | 41.5385 | 0 | -3.4615 | Slope Optimal
| 3 | 0 | 4 |  | 41 | 38.0769 | 0 | 48.4615 | Y Optimal
| 4 | 0 | 0 |  | 41 | 34.6154 | 0 | 46.4066 | Y Actual
| 5 | 0 | 0 |  | 41 | 31.1538 | 0 | 36 | X Actual
| 6 | 0 | 4 |  | 37 | 27.6923 | 0 | 14 | X Optimal
| 7 | 0 | 0 |  | 37 | 24.2308 | 0 | 1.5714 | Stream Turbulence Index
| 8 | 0 | 0 |  | 37 | 20.7692 | 0
| 9 | 0 | 0 |  | 37 | 17.3077 | 0
| 10 | 0 | 4 |  | 33 | 13.8462 | 50
| 11 | 0 | 0 |  | 33 | 10.3846 | 0
| 12 | 0 | 4 |  | 29 | 6.9231 | 0
| 13 | 0 | 0 |  | 29 | 3.4615 | 0
| 14 | 0 | 0 |  | 29 | 0 | 0
Note on L4: ElFakih, Adonis: Completed versus planned
Note on M4: ElFakih, Adonis: Remaining Story Points
Note on N4: ElFakih, Adonis: Forecasted End Date
Note on O4: ElFakih, Adonis: Stream Turbulence Index - % deviation from plan

## Instructions
How to use the Burndown Chart
Use the Burndown chart at the start of every Daily Standup Meeting (DSM) to validate and calibrate your plan, relative to an optimal plan for a sprint.
Metric shown
C/P - the ratiop of completed stories versus planned (part of the certification metrics)
REM - shows the remaining SP for the iteration as of NOW()
END - shows the copmletion date based on current progress (forecasted end dat
STI - shows the deviation from the plan where 0 is on traget and 1 is 100% off target (extracted from Agile Stream Framework)
Instructions (fill in the field marked in red)
1. Name of team
2. Iteration name/number
3. How many story points were planned in sprint planing meeting
4. Start date of iteration
5. If the PO adds/removes stories reflect them by adding or subrtacting SP in this column
6. Each day and note the number of story points "completed" as per Definition of Done